A 12-MONTH ACTION PLAN

WAKISO COMMUNITY CITY OF PEACE

Located in Bwaise

Project of Tweyambe Emergency Services

Motto: Peace Through Preparedness

1. OVERVIEW

This 12-month action plan outlines programs, timelines, outputs, responsible persons, and partners for the first operational year.

2. PROGRAM AREAS & ACTIVITIES

A. Emergency Response & Community Safety

| Month | Activity | Expected Output | Responsible parties | Partners |
| --- | --- | --- | --- | --- |
| 1 | Community hazard & safety assessment | Community risks mapped | Coordinators | LC1, community leaders |
| 2–3 | Training: Basic First Aid & CPR | 200 residents trained | Tweyambe EMS trainers | Red Cross, MOH |
| 4 | Establish 20 Community Safety Volunteers | Volunteer networks activated | Coordinator | Local youth groups |
| 6–12 | Monthly emergency awareness campaigns | 12 campaigns done | Trainers, the team and local community | Schools, churches |

B. Peace Education & Youth Empowerment

| Month | Activity | Output | Responsible parties | Partners |
| --- | --- | --- | --- | --- |
| 3 | Establish Peace Clubs in schools | 6 clubs formed | Peace Builder | Schools, teachers |
| 4–6 | Youth Peace Dialogues | 300 youth engaged | Coordinators | Local council authorities |
| 7–12 | Peace leadership mentorship | 80 youth mentored | Project Lead | NGOs, mentors |

C. Mental Health & Trauma Support

| Month | Activity | Output | Responsible parties | Partners |
| --- | --- | --- | --- | --- |
| 4–6 | Community mental health education | 400 people reached | Psychosocial support team | Health centers |
| 7–12 | Healing circles & peer support Continuous Referral pathway to psychologists | 10 circles held 40 people referred | Coordinators | Religious leaders, counselors Mental health centers NGOs |

D. Gender-Based Violence Prevention

| Month | Activity | Output | Responsible parties | Partners |
| --- | --- | --- | --- | --- |
| 2–3 | GBV hotline awareness | 1,000 residents informed | Coordinator | Police, health facilities |
| 4–7 | Men & Boys GBV Engagement Workshops | 150 men trained | Trainers | Local groups |
| 8–12 | Women’s safety & empowerment groups | 10 groups formed | Women leaders | NGOs, police family unit |

E. Drugs & Substance Abuse Prevention

| Month | Activity | Output | Responsible parties | Partners |
| --- | --- | --- | --- | --- |
| 3–6 | Anti-drug sensitization | 500 youth reached | Program Lead | Police, schools |
| 6–10 | Community Champions Against Drugs | 12 champions trained | Coordinator | NGOs |
| 9–12 | Support group referrals | 20 people referred | Coordinator | Rehab centers |

F. Environmental Peace & Clean Spaces

| Month | Activity | Output | Responsible | Partners |
| --- | --- | --- | --- | --- |
| 2–12 | Monthly clean-up | 12 clean-ups | Volunteers | Kampala City Council Authority |
| 3–8 | Flood awareness & prevention campaign | Community trained | Coordinator | National Disaster teams |
| 7–12 | Creation of 2 safe community spaces | Spaces created | Coordinator | LC1, sponsors |