| CREDIBLE INVESTMENT ORGANISATION |  |
| --- | --- |
| PEOPLE-CENTERED DEVELOPMENT APPROACH, EMPOWERING PEOPLE AND COMMUNITIES. P.O. BOX 13320, NAKURU, KENYA: EMAIL, credibleinvest@gmail.com 0722886200 |  |

09/6/2026.O. BOX 13

NAKURU Central Bussiness District INTERNATIONAL CITY OF PEACE

Strategic Action Plan (July 2026 – December 2027)

Theme:

"From Diversity to Unity: Building a Peaceful, Inclusive and Resilient Nakuru for Kenya's 2027 Elections and Beyond"

1. STRATEGIC OBJECTIVE

To establish Nakuru as a recognized International City of Peace and demonstrate that peaceful democratic transitions, social cohesion, justice, and inclusive development are achievable through collective action, evidence-based peacebuilding, and citizen participation.

2. EXPECTED IMPACT BY DECEMBER 2027

City-Level Outcomes

- Recognition of Nakuru as an International City of Peace Partner.

- One million residents engaged in peacebuilding activities.

- Peace structures operational in all 11 wards.

- Reduction of election-related tensions and violence risks.

- Increased trust among communities and institutions.

- Strong Positive Peace Index baseline and monitoring framework established.

- Nakuru positioned as a national model for peaceful elections.

National Outcomes

- Replicable peace model for Kenya.

- Contribution to peaceful 2027 elections.

- Strengthened interfaith and intercultural relations.

- Enhanced civic participation and democratic accountability.

3. STRATEGIC PILLARS

Pillar 1: Peace Governance and Coordination

Objective

Create sustainable structures for planning, coordination, implementation, and accountability.

Activities

July – September 2026

Establish:

- Nakuru International City of Peace Steering Committee

- Peace Advisory Council

- Technical Working Groups

- Ward Peace Committees

Membership:

- County Government

- National Government Administration

- Faith-Based Organizations

- Youth Representatives

- Women Leaders

- Persons with Disabilities

- CSOs

- Academia

- Business Community

- Security Agencies

- Media

Deliverables

- Governance Charter

- Terms of Reference

- Annual Work Plan

- Stakeholder Directory

Pillar 2: Positive Peace Research and Measurement

Objective

Establish a scientific evidence base for peace interventions.

Activities

August – November 2026

Conduct:

- City Peace Baseline Survey

- Ward Peace Mapping

- Social Cohesion Assessment

- Electoral Risk Assessment

- Positive Peace Assessment

Partnership

- Institute for Economics and Peace

- Universities

- Research Institutions

Outputs

- Nakuru Peace Report 2026

- Ward Peace Profiles

- Peace Dashboard

Pillar 3: Community Peace Mobilization

Objective

Reach every ward with peace awareness and engagement activities.

Activities

September 2026 – August 2027

- Community dialogues

- Open Space forums

- Peace caravans

- Cultural exchange events

- Sports for Peace

- Community clean-up campaigns

- Peace festivals

Ward Coverage

- Biashara

- Kivumbini

- Flamingo

- Menengai

- Nakuru East

- London

- Kaptembwo

- Rhoda

- Shaabab

- Barut

- Kapkures

Target

100,000 direct participants

Pillar 4: Interfaith Peace Alliance

Objective

Unite faith communities around peace and national cohesion.

Partners

- Muslim organizations

- Christian churches

- Hindu communities

- Indigenous spiritual leaders

Activities

August 2026 – October 2027

- Monthly interfaith dialogue forums

- Joint community service projects

- Peace sermons and teachings

- Peace Friday and Peace Sunday campaigns

Deliverable

Nakuru Interfaith Peace Declaration

Pillar 5: International Day of Peace 2026

Major Milestone

21 September 2026

Theme

"Our Peace, Our Future"

Activities

Peace Mural Signing Ceremony

Participation:

- Political Parties

- Religious Leaders

- Youth

- Women

- Civil Society

- Government

- Business Community

Additional Activities

- Peace Walk

- Peace Concert

- Peace Awards

- Tree Planting

- Youth Dialogue

- Cultural Performances

Target

20,000 participants

Output

Nakuru Peace Covenant 2026

Pillar 6: Election Peace Initiative

Objective

Prevent violence and strengthen democratic participation.

Timeline

January 2027 – December 2027

Activities

Peace Messaging Campaign

Communication Channels:

- Radio

- Television

- Social Media

- Community Meetings

Peace Champions Network

Recruit:

- 1,100 Peace Champions

- 100 per ward

Training Areas:

- Mediation

- Conflict Prevention

- Civic Education

- Dialogue Facilitation

Election Peace Monitoring Centre

Functions:

- Early Warning

- Rapid Response

- Information Verification

- Incident Reporting

Deliverables

- Peace Monitoring Dashboard

- Weekly Situation Reports

Pillar 7: Youth Leadership for Peace

Objective

Empower youth as peace ambassadors.

Activities

- Peace Clubs

- University Peace Forums

- Innovation Challenges

- Digital Peace Campaigns

- Creative Arts for Peace

Target

50,000 Youth

Institutions

- Universities

- TVETs

- Secondary Schools

Pillar 8: Women for Peace Initiative

Objective

Strengthen women's leadership in peacebuilding.

Activities

- Women Peace Forums

- Leadership Training

- Community Mediation Training

- Economic Empowerment Linkages

Target

20,000 Women

Pillar 9: Peace through Environment

Partners

- United Nations Environment Programme

- Kenya Forest Service

- Schools

- Community Groups

Activities

- Peace Forest Program

- Urban Greening

- Climate Action Dialogues

- Tree Growing Campaigns

Target

500,000 Trees

Pillar 10: Communication and Media for Peace

Objective

Promote responsible information sharing.

Activities

- Peace Journalism Training

- Community Radio Programs

- Social Media Campaigns

- Documentary Production

Campaign Slogan

"Peace is a Choice. Peace is Possible."

Pillar 11: International Partnerships

Strategic Partners

- International Cities of Peace

- UNESCO

- United Nations Environment Programme

- Rotary International

- Universities

- Embassies

- International NGOs

Activities

- Global Peace Webinars

- Exchange Programs

- International Conferences

- Joint Research

IMPLEMENTATION TIMELINE

| Period | Key Activity |
| --- | --- |
| Jul–Aug 2026 | Stakeholder Mobilization |
| Aug–Sep 2026 | Peace Baseline Survey |
| Sep 2026 | International Day of Peace Declaration |
| Oct–Dec 2026 | Ward Peace Structures Established |
| Jan–Mar 2027 | Peace Champions Training |
| Apr–Jun 2027 | Community Peace Campaigns |
| Jul–Aug 2027 | Election Preparedness Activities |
| Aug–Oct 2027 | Election Peace Monitoring |
| Nov–Dec 2027 | Peace Victory Celebration and Evaluation |

KEY PERFORMANCE INDICATORS (KPIs)

By December 2027

- 11 Ward Peace Committees operational.

- 1,100 trained Peace Champions.

- 100 Peace Dialogues conducted.

- 500,000 trees planted.

- 50,000 youth engaged.

- 20,000 women engaged.

- 100 faith institutions participating.

- 1 million residents reached through campaigns.

- Peace Mural signed by all major stakeholders.

- Peace Monitoring Centre operational.

- Peace Celebration held after elections.

- Nakuru recognized globally as a leading city for community-led peacebuilding.

LEGACY VISION 2030

By 2030, Nakuru will be recognized as:

"Africa's Leading City of Positive Peace, Democratic Resilience, Social Cohesion, Environmental Stewardship, and Inclusive Development."

The Nakuru model can then be replicated across Kenya's 47 counties and shared through the global network of International Cities of Peace as a practical example of how communities can transform historical divisions into a culture of peace, justice, integrity, and shared prosperity.

Partnership  with

Rafique Mohamed. CEO